SASI’s Summary of Tennessee’s Work Plan

For the Minority AIDS Initiative Funding for

Care and Prevention in the United States

(CAPUS) Demonstration Project

Background

In late September, 2012, Dr. Ronald Valdiserri, Deputy Assistant Secretary for Health, Infectious Diseases at the U.S. Department of Health and Human Services announced that 8 states, including 6 southern states (GA, LA, MS, NC, TN, VA), were awarded $14.2 million in first-year funding as part of the Care and Prevention in the United States (CAPUS) Demonstration Project. CAPUS funds are designed to reduce HIV-related morbidity, mortality, and related health disparities among racial and ethnic minorities.

A multi-agency federal partnership, including lead agency CDC and multiple HHS agencies and offices, are providing leadership and technical assistance to the grantees, who are required to use 25% of the grant funds to fund community based organizations.

In February, 2012, Dr. Valdiserri specifically credited SASI’s advocacy along with that of the 30 for 30 Campaign and PACHA for this funding initiative.   SASI’s Research Report, HIV/AIDS Epidemic in the South Reaches Crisis Proportions in Last Decade, was relied on extensively in the Funding Opportunity Announcement (FOA).

This CAPUS funding is the latest result of powerful, well-organized advocacy to deliver our message regarding the serious HIV epidemic in the Southern States.  In the past year, the Southern HIV/AIDS Strategy Initiative (“SASI”), the Southern AIDS Coalition (SAC), the 30 for 30 Campaign and many other groups and individuals have made the case for the South with the White House Office of National AIDS Policy (ONAP), at the Department of Health and Human Services (HHS), at the President’s Advisory Council on HIV/AIDS (PACHA), at the Federal AIDS Policy Partnership (FAPP) meeting, with members of Congress, and on the state and local levels. This work has been supported by multiple funders, including the Ford Foundation and AIDS United.

An Overview of the Federal CAPUS Demonstration Project

The CAPUS Demonstration Project is a funding opportunity sponsored by the Center for Disease Control and Prevention (CDC) to support programs to reduce disparities in HIV-related morbidity and mortality, and related health disparities, among minorities.

Eligible Jurisdictions

Eighteen jurisdictions were eligible to apply, with twelve jurisdictions located in the South (italicized below) and nine jurisdictions located in the Deep South.  Eligible jurisdictions were divided into three-tiers, based on HIV prevalence at year-end 2009.  Tier 1—states with HIV prevalence of at least 30,000 cases—including California, Florida, Texas, Georgia, Illinois, and Pennsylvania.  Tier 2—states with HIV prevalence of at least 16,000 cases but less than 30,000 cases—including Maryland, North Carolina, Louisiana, Puerto Rico, Ohio, Virginia.  Tier 3—states with HIV prevalence of at least 8,000 cases but less than 16,000 cases—including Tennessee, Washington, D.C., South Carolina, Missouri, Alabama, and Mississippi.

The selection of these 18 jurisdictions was based upon (1) the burden of illness, (2) disproportionality affected areas, and (3) social determinates of health.  Specifically, jurisdictions with more than 5,000 HIV cases among African Americans and Latinos, jurisdictions with an AIDS diagnosis rate of over 6 per 100,000 in 2010, and jurisdictions with a teen birth rate over 25 per 1,000 were included. (FOA, p.44)

Background

Citing the SASI report among other sources, the FOA acknowledged the disproportionate burden of HIV and AIDS in the south including high HIV fatality rates, the large numbers of HIV cases among African Americans and Latinos, high poverty levels and numbers of uninsured, healthcare provider shortages, and lower levels of educational attainment. (FOA, p. 10-11) The FOA notes the high proportion of people living with AIDS in rural and smaller urban areas, which creates limited access to HIV provider due in part to lack of reliable transportation and pervasive HIV-related stigma. (FOA p. 11)

Grantees

Eight states were funded with a total of approximately $14.2 million in year one, including six Southern states.  Grantees are Georgia, Illinois, Louisiana, Mississippi, Missouri, North Carolina, Tennessee, and Virginia.  Alabama, South Carolina, and Texas applied but were not awarded funding.

Table 1: CAPUS Funding for FY 2012

| Georgia Dept. of Public Health | 2,524,266 |
| --- | --- |
| Illinois Dept. of Public Health | 2,524,266 |
| Virginia State Dept. of Health | 1,897,500 |
| Louisiana State Dept. of Health & Hospitals | 1,897,500 |
| North Carolina Dept. of Health & Human Services | 1,897,500 |
| Missouri Dept. of Health & Senior Services | 1,164,137 |
| Mississippi State Dept. of Health | 1,164,137 |
| Tennessee State Dept. of Health | 1,164,137 |
| Total | $14,233,422 |

TENNESSEE CAPUS OVERVIEW

As a participant in the Secretary’s Minority AIDS Initiative Funding for Care and

Prevention in the United States (CAPUS) Demonstration Project, the Tennessee Department of Health (TDH) has planned several activities designed to strengthen and support the following goals in Tennessee (TN): 1)Earlier identification of HIV-infected individuals in clinical and non-clinical settings; 2) Immediate linkage to care for newly diagnosed HIV positive individuals; 3)Retention in, re-engagement into, and optimal response to care for known HIV positive individuals; 4) Identify and address key social and structural factors directly affecting the preceding goals.

Key Elements of Tennessee CAPUS:

- The introduction of the Association of Public Health Laboratories (APHL) / CDC proposed 4th generation HIV testing algorithm in TN’s state laboratories.

- A Social Networking Strategy (SNS) employed among men who have sex with other men (MSM), with a focus on Black MSM.

- A Corrections Navigation program, facilitating the transfer of inmates to HIV care and treatment in the community upon release.

- The use of surveillance data to equip Disease Intervention Specialists (DIS) and Case Managers to:

  - Identify and locate known HIV positive individuals who have been out of care for > 1 year and facilitate their re-engagement into HIV care

  - Identify and inform providers of their HIV positive clients who are in care but not achieving optimal virologic and/or immunologic response to care

Tennessee’s CAPUS activities are designed to fill existing service gaps and complement existing HIV Prevention activities.

SPECIFIC TENNESSEE CAPUS OBJECTIVES/ACTIVITIES

1. Use of Surveillance Data and Data Systems to Improve Care and Prevention

- Expand the use of laboratory surveillance data for programmatic improvement

- Goal 1.1: Identify persons living with HIV who have never been in care or who have been out of care and successfully re-engage them with HIV medical care services

  - By 10/2013 (after 1 quarter of implementation), TDH CAPUS DIS Re-Engagement Case Managers will have re-engaged back into care 123 persons identified as being not in care during the previous 1-year calendar period.

    - Hire key CAPUS re-engagement personnel.

    - Identify persons not in care utilizing eHARS quarterly reports.

    - Re-engage persons in care by identifying and having DIS follow up with those who have been out of care for at least a year.

- Goal 1.2: Improve suboptimal clinic outcomes for persons in care

  - By 12/2015 (consistent with TN HAS 2015 goals), the rate of persons diagnosed with HIV in care (as evidenced by ≥ 1 viral load in eHARs) who are virally suppressed will increase from 74% to 80%.

    - Identify person in care without viral suppression.

    - Provide medical providers with a list of their in-care clients who are failing to achieve viral suppression.

B.	Enhance laboratory data systems reporting of tests related to HIV diagnosis, CD4+ T-lymphocyte count, and HIV viral load (VL)

- Goal 1.3: Enhance viral load and CD4 count reporting into eHARS

  - By 12/2013, TDH will increase the number of commercial laboratories with electronic laboratory reporting from 3 to 4.

    - Bring commercial laboratories onboard through promotion of electronic testing.

  - By 12/2013, TDH will increase the number of hospital laboratories reporting comprehensive HIV data by 2.

    - Bring additional hospitals on board by contacting 2 hospitals that do not appear to be reporting comprehensive HIV CD4 and VL data to THD (St. Jude Hospital in Memphis and Vanderbilt University Hospital in Nashville.)

    - Establish reporting practices to ensure that these labs are comprehensively reported to TDH’s central surveillance office.

  - By 7/2013, TDH will manually enter reported VL and CD4 data in eHARS

    - Hire 2 full-time data entry clerks.

- Goal 1.4: Assess completeness and timeliness of laboratory data reporting

  - By 12/2013 (after 2 quarters of implementation), ≥ 95% of newly diagnosed HIV infections will be reported to TDH within 3 months of test date.

    - Measure completeness of lab data for all newly diagnosed HIV cases through assessments by the HAS data coordinator

  - By 12/2013 (after 2 quarters of implementation), ≥95% of HIV lab results will be reported by TDH within 3 months of test date.

    - Measure the timeliness of lab data for newly diagnosed HIV cases and for viral load (VL) and CD4 data.

- Goal 1.5: Monitor and report on electronic lab reporting (ELR) and manual data entry

  - By 12/2013 (after 2 quarters of implementation), TDH will monitor the proportion of HIV labs received that are entered into eHARS via ELR.

C.	Facilitate the routine use of laboratory surveillance data

- Goal 1.6: Monitor clinical outcomes along with the continuum of care

  - By 08/2013, TDH’s HIV/STD medical director will develop a statewide HIV continuum of care based on 2010 HIV surveillance data.

    - Analysis of statewide HIV continuum of care data based on pre-established criteria by TDH’s HIV/STD Medical Director.

    - TDH’s Medical Director will present TN’s 2010 Continuum of HIV Care data in the form of a White Paper, which will be updated and monitored annually.

2. Increase HIV Testing, Entry, Linkage, Retention, and Reengagement with Care, Treatment and Prevention

D.	Increase collaboration between care and prevention programs and HIV surveillance programs

A. Increase the identification of HIV infections in clinical and non-clinical settings and identify HIV earlier in the course of infection

- Goal 2.1: Implement the Social Network Strategy (SNS) to encourage HIV testing among hard to reach African American men who have sex with men (AA MSM) in Memphis and Nashville with an overall goal of a 5% sero-positivity rate for the SNS activity.

  - By 04/2013, TDH will execute contracts with three community-based organizations (CBO) to implement SNS in Memphis and Nashville

    - Three CBOs will be contracted to implement the strategy and will hire a full-time SNS Tester at each facility.

  - By 10/2013 (after 1 quarter of implementation), CBOs will conduct (utilizing SNS) a total of 150 HIV tests in Memphis and 75 HIV tests in Nashville, with a sero-positivity rate of 5%.

    - Testing will be conducted by CBO SNS coordinators. Each CBO will be expected to conduct 25 tests per month, and identify at least 4 recruiters each month.

    - Each man tested will be offered a $20 incentive for participating in the SNS HIV testing program.

  - By 10/2013 (1 quarter after implementation), provide at least 90% of clients receiving a new diagnosis through SNS with their test results.

    - Testing will be done primarily using oral fluid rapid test and clients will receive preliminary results within 20 minutes.

- Goal 2.2: Introduce APHL/CDC proposed 4th generation HIV testing algorithm.

  - By 04/2013, TDH will begin using 4th generation HIV testing algorithm in Tennessee state laboratories.

    - Tennessee state laboratory director will solicit bids for a contract from companies who produce 4th generation reagents and will enter into a contract with the lowest bidder.

- Goal 2.3: Link newly diagnosed AA MSM men into HIV medical care.

  - By 10/2013 (after 1 quarter of implementation), 80% of newly diagnosed AA MSM will be provided with linkage to care services by the Early Intervention Specialist (EIS) in a single session.

    - An EIS at each of the CBOs (funded through the Ryan White Part A program) will link a person testing HIV positive to care in a single session through a specific protocol and quality assurance system.

    - The SNS coordinator will be responsible for cross-checking new positives with the Part A grantees to ensure EIS services were provided on a quarterly basis.

  - By 10/2013 (after 1 quarter of implementation), 80% of AA/Black MSM who are newly diagnosed will be linked into HIV medical care within 3 months of diagnosis.

    - CBO staff will refer newly positive clients to the EIS at their agency funded by the Ryan White Part A grantee and TDH’s SNS coordinator will follow up.

  - By 10/2013 (after 1 quarter of implementation), 80% of newly diagnosed AA MSM will be linked to partner and prevention services within 1 month of diagnosis

    - CBO SNS testers will report each client who tests positive to their county health department for Partner Services.

- Goal 2.4: Link those tested through SNS into other prevention services, including substance abuse and mental health treatment, as needed

  - By 10/2013 (after 1 quarter of implementation), 50% of new positives will be referred for other HIV prevention activities and to non-HIV related behavioral health services.

    - SNS staff will be trained to recognize clients who fit risk criteria for CDC’s effective behavioral interventions (DEBIs) and will be instructed to make proper referrals.

    - SNS staff will also be trained using the 6 steps of HIV Prevention Counseling to recognize opportunities and needs for referral into other social service programs during their risk assessment interview process.

3. Create Statewide Patient Navigation System to Improve Care, Linkage, Retention, Reengagement, and Viral Suppression

A. The TDH Navigation Model/Approach and roles of navigators in improving linkage to, retention in, and re-engagement with HIV and related care, treatment, prevention, behavioral health services, and other services.

- Goal 3.1: Use correctional navigators to facilitate linkage into HIV treatment in the community for persons living with HIV prior to their release from jail/prison.

  - By 10/2013 (after 1 quarter of implementation), provide 40 inmates living with HIV with navigation services to assist them with linkage to medical care within the community upon release.

    - By 8/2013, TDH contractors will hire and train 3 full-time Corrections Navigators (CNs) (1 in East TN, 1 in Middle TN, and 1 in West TN) in motivational interviewing.

    - CN’s will meet with administrative and clinical staff at the correctional facilities within their region to introduce the Navigation program.

    - TDH will produce standard “linkage starter packs” that will be provided to all corrections providers.

    - CNs will coordinate meetings between facilities’ correctional medical staff to meet with inmates prior to release to ascertain where the clients anticipate relocating, review the information in the “linkage start packs,” and work with the inmates to establish medical appointments in the communities in which they plan to relocate.

    - Provide individuals participating in the corrections navigation program with incentives.

  - By 10/2013 (after 1 quarter of implementation), 70% of inmates provided with corrections navigation services will be linked to medical care in the community within 3 months of release.

4. Address Social and Structural Factors Directly Affecting HIV Testing, Linkage to, Retention in, and Reengagement with Care, Treatment and Prevention

A.	Use epidemiologic data to identify the racial and ethnic communities disproportionately affected by HIV and related diseases within the jurisdiction.

- Goal 4.1: To address issues of cultural mistrust, homophobia, and stigma that affect testing, linkage, retention and/or re-engagement into care and prevention services

  - By November, 2013 40 health department staff will demonstrate an increase in knowledge and skills of social and structural barriers, including cultural mistrust, homophobia, and stigma, and their relationship to HIV testing and treatment as demonstrated through post-test assessments in training.

  - By March, 2014, at least 50 CBO staff from collaborating agencies will demonstrate an increase in knowledge and skills of social and structural barriers, including cultural mistrust, homophobia, and stigma, and their relationship to HIV testing and treatment as demonstrated through post-test assessment in training.

    - Work with CAPUS site team to identify and submit a capacity building request with CDC/DHAP/CBB.

    - By 2/2014, conduct a pre-evaluation with training participants prior to the training to assess their understanding of cultural mistrust/stigma (HIV and homophobia), and how it affects HIV testing, linkage, retention and re-engagement into care.

    - By 3/2014, evaluate knowledge and skills through post-evaluation surveys.

    - By 10/2014, convene meeting with CBO or health care service provider to discuss how the training has impact their work.

- Goal 4.2: To reduce structural barriers related to employment and housing that affect linkage, retention and/or re-engagement into care among AA men.

  - By 12/2013, TDH will work with community partners and stakeholders to develop a plan to refer persons reached through SNS or the correction navigation program who have identified employment as a barrier to linkage, retention and re-engagement.

  - By 4/2014 (after 1 quarter of implementation), provide referrals to 100% of clients (who have identified a need for employment) reached through SNS or corrections navigation to community based programs designed to overcome employment barriers.

  - By 4/2014 (after 1 quarter of implementation), provide referrals to 100% of clients (who have identified a need for housing) reached through SNS or corrections navigation to community based programs designed to overcome housing barriers.

    - By 8/2013, identify job placement organizations to determine what services they can provide.

    - By 12/2013, convene a meeting with community partners and stakeholders to strategize about how to maximize job placement resources for person recently released from jail and living with HIV and clients reached through SNS.

    - By 12/2013, develop brochures summarizing available support services available in the community (including community-based programs providing medical case management, counseling, mental health, substance abuse, housing, and transport services.)

    - By 12/2013, TDH will partner with existing providers to facilitate the addition of housing and other services as referral tools to address social and structural barriers that prevent clients from accessing HIV medical are within 180 days.

    - By 1/2014, CNs and CBO SNS staff begin submitting monthly reports for their jurisdiction to the centrally located HAS Data Coordinator .

Community Based Organizations Awards

- TDH will collaborate with five CBOs (3 for SNS and 3 for Corrections Navigators, with one CBO participating in both activities) across the state to address the SNS testing component and the immediate linkage to care activity involving Corrections Navigators. These CBOs have worked with TDH in the past and have a good standing relationship with the HIV Prevention section. The CBOs were chosen based on their past history of HIV testing in the MSM community (for SNS) and their past history of working in corrections (for the corrections liaisons.) Tennessee has a limited number of CBOs that target MSMs and work actively in corrections, so TDH determined it was unnecessary to create an RFP process.

Taken from Tennessee’s CAPUS work plan, August 19, 2013

Enhanced HIV/AIDS Reporting System (eHARS) is a browser-based application provided by the CDC.